## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 42
PROJECT NAME | Intelligent Wardrobe Management System
PROJECT MENTOR (sponsor) | Dr Neeta Gulati
TEAM MEMBERS | Shaunak Biswas
Vansh Motwani
Harpreet Singh
Jayesh Sutar
Raveesh Vyas

## Status
PROJECT NUMBER | 42
PROJECT NAME | Intelligent Wardrobe Management System
PROJECT MENTOR (sponsor) | Dr. Neeta Gulati
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meet-1 with the client | Coordination | Bhav Beri | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Shaunak Biswas | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting(17-01-24) | Coordination | Bhav Beri | 5 | 5.5 | Done | Make sure scoping questions are included | -0.5 | 9.0909
Research existing technology | Preparation | Whole Team | 2 | 1.5 | Done | Decided on MERN stack | 0.5 | 33.3333
Meet 2 Document | Preparation | Shaunak Biswas | 1 | 0.75 | Done |  | 0.25 | 33.3333
Team Meeting | Coordination | Harpreet Singh | 5 | 4 | Done |  | 1 | 25
Status tracker | Documentation | Jayesh Sutar | 1 | 1.1 | Done |  | -0.1 | 9.0909
Week 2 (January 22 - January 28)
Client meeting-2(22-01-24) | Coordination | Shaunak Biswas | 4.1 | 3.75 | Done |  | 0.35 | 9.3333
Team Meeting (23-01-24) | Coordination | Shaunak Biswas | 5 | 5.5 | Done |  | -0.5 | 9.0909
Project synopsis writeup | Documentation | Shaunak Biswas | 1 | 1.2 | Done | Part of the 25th January submission | -0.2 | 16.6667
Requirement Document writeup | Documentation | Raveesh Vyas | 1 | 0.5 | Done |  | 0.5 | 100
Project Plan Document | Documentation | Vansh Motwani | 1 | 1.2 | Done | Part of the 31st January submission | -0.2 | 16.6667
Initial UI Structuring | Design | Harpreet Singh | 1 | 1 | Done | Part of the 25th January submission | 0 | 0
Learn Figma | Preparation | Harpreet Singh, Shaunak Biswas | 6 | 7 | Done |  | -1 | 14.2857
Status tracker | Documentation | Jayesh Sutar | 1 | 1 | Done |  | 0 | 0
Product Pitch | Design | Shaunak Biswas | 2 | 3 | Done |  | -1 | 33.3333
Team Meeting (24-01-24) | Coordination | Raveesh Vyas | 5 | 7.2 | Done | Discussion on AWS options | -2.2 | 30.5556
Week 3 (January 29 - February 4)
Product Pitch Modification | Design | Shaunak Biswas | 1 | 1.5 | Done | wanted by Client | -0.5 | 33.3333
meet with Interns(01-02-24) | Coordination | Vansh Motwani | 5 | 5 | Done | Discussion on ML models | 0 | 0
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.75 | Done |  | -0.25 | 33.3333
Requirement Analysis | Requirements | Harpreet Singh, Raveesh Vyas | 8 | 10 | Done |  | -2 | 20
Week 4 (February 5 - February 11)
Status Tracker | Documentation | Shaunak Biswas | 0.5 | 0.5 | Done |  | 0 | 0
Team Meet (09-02-2024) | Coordination | Harpreet Singh | 3 | 3 | Done | Discussion on Requirements Specification partioning | 0 | 0
Requirements Specification Modules | Requirements | Whole Team | 10 | 9 | Done | Creation of SRS as 3 modules: App, Website and Backend | 1 | 11.1111
Week 5 (February 12 - Feburary 18)
Status tracker | Documentation | Shaunak Biswas | 0.75 | 0.75 | Done |  | 0 | 0
SRS Use Cases | Requirements | Jayesh Sutar | 4 | 4.25 | Done | As an extension to the SRS | -0.25 | 5.8824
SRS User Stories | Requirements | Shaunak Biswas | 3 | 3.5 | Done | As an extension to the SRS | -0.5 | 14.2857
UI Finalize Basic Outline | Design | Vansh Motwani | 7 | 7.2 | Done |  | -0.2 | 2.7778
Final UI Interface on Figma | Design | Harpreet Singh, Raveesh Vyas | 20 | 18 | Done |  | 2 | 11.1111
Learn React & React Native Basics | Preparation | Whole Team | 40 | 45 | Done |  | -5 | 11.1111
Intern Meet | Coordination | Jayesh Sutar | 3.5 | 3.33 | Done | Discussion on Signup Data and Trend Analysis | 0.17 | 5.1051
UML use case and class diagram | Documentation | Jayesh Sutar,Harpreet Singh | 3 | 3.5 | Done |  | -0.5 | 14.2857
Client Meet | Coordination | Shaunak Biswas | 0.5 | 0.5 | Done |  | 0 | 0
Week 6 (February 19 - February 25)
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.5 | Done |  | 0 | 0
Test plan tracker | Testing | Whole Team | 7.5 | 8 | Done |  | -0.5 | 6.25
Meet with client and AI expert | Coordination | Whole Team | 1.5 | 1.6 | Done | Session with Microsoft AI expert | -0.1 | 6.25
App home and wardrobe page | Development | Jayesh sutar,Shaunak Biswas | 16 | 12 | Done |  | 4 | 33.3333
App recommendation page | Development | Vansh Motwani | 9 | 6.5 | Done |  | 2.5 | 38.4615
App sign In,sign up and profile customization page | Development | Harpreet Singh, Raveesh Vyas | 18 | 18 | Done |  | 0 | 0
Week 7 (February 26- March 3)
Status tracker | Documentation | Shaunak Biswas | 0.5 | 0.5 | Done |  | 0 | 0
Learn MongoDB | Preparation | Whole Team | 10 | 8 | Done |  | 2 | 25
MongoDB Atlas Setup | Development | Jayesh Sutar | 2 | 3 | Done
User login info database | Development | Vansh Motwani, Shaunak Biswas | 6 |  | Delayed
Team Meet | Coordination | Harpreet Singh | 5 | 4 | Done
Client Meet | Coordination | Raveesh Vyas | 4 |  | Delayed | tentatively, 2/3/24
Week 8 (March 4- March 10)
Status tracker | Documentation | Shaunak Biswas,Jayesh Sutar | 0.5 | 0.5 | Done |  | 0 | 0
Client Meet | Coordination | Whole Team | 5 |  | Planned | shifted from 2nd to 4th March
User Profile info database | Development | Harpreet,Raveesh,Vansh | 18 |  | Planned
google Signup Intergration | Development | Harpreet,Raveesh | 10 |  | Planned
User login info database | Development | Jayesh sutar,Shaunak Biswas | 10 |  | Planned
Team Meet | Coordination | Whole Team | 5 |  | Planned
Design Document | Documentation | Shaunak,Vansh,Jayesh | 9 |  | Planned
Week 9
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically