## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 42
PROJECT NAME | Intelligent Wardrobe Management System
PROJECT MENTOR (sponsor) | Dr Neeta Gulati
TEAM MEMBERS | Shaunak Biswas
Vansh Motwani
Harpreet Singh
Jayesh Sutar
Raveesh Vyas

## Status
42
Intelligent Wardrobe Management System
Dr. Neeta Gulati
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meet-1 with the client | Coordination | Bhav Beri | 0.5 | 0.3 | Done
GIT Repository setup | Preparation | Shaunak Biswas | 1 | 1.5 | Done
Client meeting(17-01-24) | Coordination | Bhav Beri | 5 | 5.5 | Done | Make sure scoping questions are included
Research existing technology | Preparation | Whole Team | 2 | 1.5 | Done | Decided on MERN stack
Meet 2 Document | Preparation | Shaunak Biswas | 1 | 0.75 | Done
Team Meeting | Coordination | Harpreet Singh | 5 | 4 | Done
Status tracker | Documentation | Jayesh Sutar | 1 | 1.1 | Done
Week 2 (January 22 - January 28)
Client meeting-2(22-01-24) | Coordination | Shaunak Biswas | 4.1 | 3.75 | Done
Team Meeting (23-01-24) | Coordination | Shaunak Biswas | 5 | 5.5 | Done
Project synopsis writeup | Documentation | Shaunak Biswas | 1 | 1.2 | Done | Part of the 25th January submission
Requirement Document writeup | Documentation | Raveesh Vyas | 1 | 0.5 | Done
Project Plan Document | Documentation | Vansh Motwani | 1 | 1.2 | Done | Part of the 31st January submission
Initial UI Structuring | Design | Harpreet Singh | 1 | 1 | Done | Part of the 25th January submission
Learn Figma | Preparation | Harpreet Singh, Shaunak Biswas | 6 | 7 | Done
Status tracker | Documentation | Jayesh Sutar | 1 | 1 | Done
Product Pitch | Design | Shaunak Biswas | 2 | 3 | Done
Team Meeting (24-01-24) | Coordination | Raveesh Vyas | 5 | 7.2 | Done | Discussion on AWS options
Week 3 (January 29 - February 4)
Product Pitch Modification | Design | Shaunak Biswas | 1 | 1.5 | Done | wanted by Client
meet with Interns(01-02-24) | Coordination | Vansh Motwani | 5 | 5 | Done | Discussion on ML models
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.75 | Done
Requirement Analysis | Requirements | Harpreet Singh, Raveesh Vyas | 8 | 10 | Done
Week 4 (February 5 - February 11)
Status Tracker | Documentation | Shaunak Biswas | 0.5 | 0.5 | Done
Team Meet (09-02-2024) | Coordination | Harpreet Singh | 3 | 3 | Done | Discussion on Requirements Specification partioning
Requirements Specification Modules | Requirements | Whole Team | 10 | 9 | Done | Creation of SRS as 3 modules: App, Website and Backend
Week 5 (February 12 - Feburary 18)
Status tracker | Documentation | Shaunak Biswas | 0.75 | 0.75 | Done
SRS Use Cases | Requirements | Jayesh Sutar | 4 | 4.25 | Done | As an extension to the SRS
SRS User Stories | Requirements | Shaunak Biswas | 3 | 3.5 | Done | As an extension to the SRS
UI Finalize Basic Outline | Design | Vansh Motwani | 7 | 7.2 | Done
Final UI Interface on Figma | Design | Harpreet Singh, Raveesh Vyas | 20 | 18 | Done
Learn React & React Native Basics | Preparation | Whole Team | 40 | 45 | Done
Intern Meet | Coordination | Jayesh Sutar | 3.5 | 3.33 | Done | Discussion on Signup Data and Trend Analysis
UML use case and class diagram | Documentation | Jayesh Sutar,Harpreet Singh | 3 | 3.5 | Done
Client Meet | Coordination | Shaunak Biswas | 0.5 | 0.5 | Done
Week 6 (February 19 - February 25)
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.5 | Done
Test plan tracker | Testing | Whole Team | 7.5 | 8 | Done
Meet with client and AI expert | Coordination | Whole Team | 1.5 | 1.6 | Done | Session with Microsoft AI expert
App home and wardrobe page | Development | Jayesh sutar,Shaunak Biswas | 16 | 12 | Done
App recommendation page | Development | Vansh Motwani | 9 | 6.5 | Done
App sign In,sign up and profile customization page | Development | Harpreet Singh, Raveesh Vyas | 18 | 18 | Done
Week 7 (February 26 - March 3)
Status tracker | Documentation | Shaunak Biswas | 0.5 | 0.5 | Done
Learn MongoDB | Preparation | Whole Team | 10 | 8 | Done
MongoDB Atlas Setup | Development | Jayesh Sutar | 2 | 3 | Done
User login info database | Development | Vansh Motwani, Shaunak Biswas | 6 |  | Delayed
Team Meet | Coordination | Harpreet Singh | 5 | 4 | Done
Client Meet | Coordination | Raveesh Vyas | 4 |  | Delayed | tentatively, 2/3/24
Week 8 (March 4 - March 10)
Status tracker | Documentation | Shaunak Biswas,Jayesh Sutar | 0.5 | 0.5 | Done
Client Meet (04-03-2024) | Coordination | Whole Team | 5 | 4.5 | Done | shifted from 2nd to 4th March
User Profile info database | Development | Harpreet,Raveesh,Vansh | 18 | 15 | Done
User login info database | Development | Jayesh sutar,Shaunak Biswas | 10 | 9 | Done
Team Meet (05-03-2024) | Coordination | Whole Team | 5 | 4 | Done
Client Meet (09-03-2024) | Coordination | Whole Team | 4 | 3.75 | Done | Met new MLinterns
Team Meet (10-03-2024) | Coordination | Whole Team | 7 | 7.5 | Done
Design Document | Documentation | Shaunak,Vansh,Jayesh | 9 | 7.5 | Done
Week 9 (March 11 - March 17)
Status tracker | Documentation | Shaunak Biswas | 0.4 | 0.4 | Done
Client Meet (14-03-2024) | Coordination | Whole Team | 5 | 5 | Done | Dataset availability for classification model was discussed
Team Meet | Coordination | Whole Team | 5 | 5.5 | Done
Finalize React Framework | Preparation | Vansh Motwani | 1 | 0.8 | Done
Website UI Alterations | Design | Shaunak Biswas, Jayesh Sutar | 8 | 6 | Done
Website User Profile | Development | Raveesh Vyas | 7 | 6 | Done
Website Login & Signup Page | Development | Vansh Motwani | 6 | 6 | Done
Website Home Page and Navigation | Development | Harpreet Singh | 8 | 7.5 | Done
Website Wardrobe Page | Development | Shaunak Biswas, Jayesh Sutar | 10 | 11 | Done
App Testing | Testing | Jayesh Sutar, Shaunak Biswas | 18 | 15 | Done | testing for R1 part
Website Testing | Testing | Raveesh Vyas | 12 | 10 | Done | testing for R1 part
Week 10 (March 18 - March 24)
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.5 | Done
Website wardrobe feature completion | Development | Vansh Motwani,Harpreet Singh | 10 | 11 | Done
App deactivate account option | Development | Shaunak Biswas | 3 | 3 | Done
Forgot password feature | Development | Raveesh Vyas | 5 |  | Delayed
Mail server setup for forgot password | Development | Shaunak Biswas, Jayesh Sutar | 8 |  | Delayed
Change password feature | Development | Jayesh Sutar | 4 | 4 | Done
Client Meet | Coordination | Whole Team | 5 |  | Delayed | client was busy with the schedule so meet will be held in next week
Team meet | Coordination | Whole Team | 5 | 5 | Done
Week 11 (March 25 - March 31)
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.5 | Done
Team meet | Coordination | Whole Team | 5 | 4.5 | Done
Client Meet | Coordination | Whole Team | 5 | 5.5 | Done | New intern joined to build the ML model
Mail server setup for forgot password | Development | Shuanak Biswas, Jayesh Sutar | 8 | 8 | Done
Forgot password feature | Development | Raveesh Vyas | 5 | 4 | Done
Website Trends page | Development | Vansh Motwani,Harpreet Singh | 4 | 5 | Done
Website Recommendation | Development | Shuanak Biswas, Jayesh Sutar | 5 |  | Delayed
Week 12 (April 1 - April 7)
Status tracker | Documentation | Jayesh Sutar | 0.5 | 0.5 | Done
Team meet | Coordination | Whole Team | 5 | 4 | Done
Website Recommendation | Development | Shaunak Biswas, Jayesh Sutar | 8 | 6 | Done
Computer Vision Research | Development | Harpreet Singh | 4 | 6 | Done
Extension of Forgot password feature for website | Development | Raveesh Vyas,Vansh Motwani | 4 |  | Delayed
Client meet | Coordination | Whole Team | 5 |  | Delayed
Week 13 (April 8 - April 14)
Status tracker | Documentation | Raveesh Vyas | 0.5 | 0.5 | Done
Client Meet | Coordination | Whole Team | 5 | 5 | Done
Outfit Identitfication (Computer Vision) | Development | Harpreet Singh | 8 | 7 | Done
Outfit Recommendation word2vec | Development | Raveesh Vyas | 10 | 7.5 | Done
Colour Identification Model (Computer Vision) | Development | Shaunak Biswas | 6 | 5 | Done
Team Meet | Coordination | Whole Team | 5 | 5 | Done
Deactivate Account Feature | Development | Jayesh Sutar | 6 | 5.5 | Done
Week 14 (April 15 - April 21)
Status tracker | Documentation | Shaunak Biswas | 0.5 | 0.5 | Done
Client Meet | Coordination | Whole Team | 5 |  | Planned
Microsoft Azure Deployment Meet | Coordination | Whole Team | 5 |  | Planned | Scheduled for Sunday to hand over code for deployment
Outfit Identification Integration | Development | Vansh Motwani,Harpreet Singh | 8 |  | Planned
Outfit Recommendation Integration | Development | Raveesh Vyas | 10 |  | Planned
Trend Analysis Scraping | Development | Harpreet Singh | 8 |  | Planned | Pending deiscussion of copyright issues
Trend Analysis Integration | Development | Vansh Motwani | 6 |  | Planned
Team Meet | Coordination | Whole Team | 5 |  | Planned
Extension of Forgot password feature for website | Development | Jayesh Sutar,Vansh Motwani | 4 |  | Planned
Recommendation Waiting Screen | Development | Jayesh Sutar, Shaunak Biswas | 8 |  | Planned
Code Testing | Testing | Whole Team | 20 |  | Planned