## TestPlan
Test Planner and Tracker |  |  | Team 42 | Shaunak Biswas, Vansh Motwani, Jayesh Sutar, Harpreet Singh, Raveesh Vyas
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
APP: | [8 empty] | Outcome as desired
Outcome not desired
1 | Signing Up | The user is not logged in to the system in the App. | User attempts to sign up. User fails to provide email ID which is a mandatory field. | The system displays an error message prompting the user to fill in all required fields. | An error message "Fill out all fields" is displayed |  | An error message "Email is a required filed " is displayed |  | Desired outcome changed
2 | Signing Up | The user is not logged in to the system in the App. An account by the email ID of temp@gmail.com already exists. | User attempts to sign up with temp@gmail.com as their email. | The system displays an error message indicating that the email is already in use. | An error message "User already exists" is displayed |  | An error message "User already exist" is displayed
3 | Signing Up | The user is not logged in to the system. | User successfully fills out the sign-up form with all required information. | The system creates a new user account and automatically logs in the user. | User redirected to the signin page |  | User redirected to the signin page
4 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded atleast 1 clothing item classified as Casualwear. | User navigates to the 'Wardrobe’ section and selects 'Casualwear' from the filter tags. | The system retrieves and displays the user's Casualwear clothes, as assigned by the ML model. | The user is displayed all clothes of the given tag |  | The user is displayed all clothes of the given tag
5 | Viewing Clothing Collection | The user is not logged in to the system. | User opens the app. | The system displays the current trending images to the user and prompts to login. | The trending images are not seen on the home page. |  | Current trending images are displayed and login button is displayed.
6 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded no clothing images yet. | User navigates to the "Clothing Collection" section. | The system prompts the user to upload clothing images. An 'Add New' button is presented. | 'Add new’ button is there but no prompt is shown. |  | A prompt is shown to tell the user to add their clothing items by pressing + which is Add New button.
7 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded no clothing item classified as casualwear. | User navigates to the 'Clothing Collection' section. User selects 'Casualwear' from the filter tags. | The system displays a message that no clothes match the given description. | No cloth items shown |  | The system displays a message that no clothes match the given description.
8 | Adding New Clothing Items | The user is logged in on the mobile app. | The user clicks on the 'Add New' button. | The user is presented with the options 'Camera' and 'Gallery'. | The user can click a photo or upload from gallery |  | The user can click a photo or upload from gallery
9 | Adding New Clothing Items | The user is logged in on the mobile app. | User navigates to the "Wardrobe" section. The user clicks on the '+' button. | The user is presented with the options 'Camera' and 'Gallery'. | The user can click a photo or upload from gallery |  | The user can click a photo or upload from gallery
10 | Adding New Clothing Items | User is logged in and has added clicked + button to add a new clothing item. | User clicks on the 'Camera' option. The user's camera app opens. The user clicks an image. The user clicks on the tick mark when shown the image captured. | The item is displayed on the 'Clothing Collection' section of the application, with tags assigned by the ML model. | The captured image is added to user's wardrobe. Random tags shown. |  | The captured image is added to the user’s wardrobe and tags assigned by ML model are shown.
11 | Adding New Clothing Items | User is logged in and has added clicked + button to add a new clothing item. | User clicks on the 'Camera' option. The user's camera app opens. The user clicks an image. The user clicks on the cross mark when shown the image captured. | The image is discarded and the user returns back to the 'Clothing Collection' page. | The image is not added, and user can click another picture |  | The image is not added, and user can click another picture.
12 | Adding New Clothing Items | User is logged in and has added clicked + button to add a new clothing item. | User clicks on the 'Gallery' option. The gallery app opens. The user selects an image. | The image is displayed on the 'Clothing Collection' section of the application, with tags assigned by the ML model. | The captured image is added to user's wardrobe. Random tags given |  | The captured image is added to the user’s wardrobe and tags assigned by ML model are shown.
13 | Deleting Clothing Items | There is atleast one clothing item present in wardrobe. | User presses the delete icon present on clothing item. User selects 'Yes' when prompted 'Are you sure?' | The selected item is successfully removed from database. The wardrobe updates immediately to reflect the removal of deleted item. | The item is deleted from user's wardrobe |  | The item is deleted from user's wardrobe
14 | Deleting Clothing Items | There is atleast one clothing item present in wardrobe. | User presses the delete icon present on clothing item. User selects 'No' when prompted 'Are you sure?' | The wardrobe remains unaffected. | The item is not deleted from user's wardrobe |  | The item is deleted from user's wardrobe
15 | User Profile Customization | The user is logged in to the system. The user's password is 'abcdef' | User goes to 'Customize profile'. User selects 'Change password' option. User enters wrong old password, 'ABCDEF' | An error message "Wrong password" is displayed. The user is prompted to enter password again | Part of R2 submission |  | An error message "Wrong Old password" is displayed. The user is prompted to enter password again.
16 | User Profile Customization | The user is logged in to the system. The user's password is 'abcdef' | User goes to 'Customize profile'. User selects 'Change password' option. User enters correct old password 'abcdef', and a new password '123456' | The password of the profile is updated in the database to '123456' | Part of R2 submission |  | The password of the profile is updated in the database to '123456'
17 | User Profile Customization | The user is logged in to the system. The user's gender is set as Male. | User goes to Profile Page. User selects 'Other' as updated gender. The user saves changes. | The gender of the profile is updated in the database. | The gender of user is changed |  | The gender of user is changed
18 | User Profile Customization | The user is logged in to the system. The user's phone number is 9898989898. | User goes to Profile Page. In the mobile number field, user enters a 10 digit number, 9898989897. The user saves changes. | The phone number of the profile is updated in the database. | The phone number of user is changed |  | The phone number of user is changed
19 | User Profile Customization | The user is logged in to the system. The user's phone number is 9898989898. | User goes to Profile Page. In the mobile number field, The user enters a 9 digit number, 989898987. | An error message "Invalid Phone number" is displayed and the user is prompted to enter phone number again | An error message "Invalid field mobile" is displayed |  | An error message "Invalid field mobile" is displayed
20 | User Profile Customization | The user is logged in to the system. The user's name is set as 'Amit'. | User goes to Profile Page. In the Name field, The user enters a non-empty name, Amitabh. The user saves changes. | The name of the user is updated in the database | The name of the user is updated |  | The name of the user is updated
21 | Signing In | The user is not logged in to the system. | User enters valid email ID. User enters correct password. User presses Submit button. | User successfully logs in into the account | The user is logged in and is on home page |  | The user is logged in and is on home page
22 | Signing In | The user is not logged in to the system. | User enters invalid email. User preses submit button. | An error message "Invalid email or password!" | An error message "Email not registered" is displayed |  | An error message "Email not registered" is displayed
23 | Signing In | The user is not logged in to the system. | User enters valid email and incorrect password. User presses submit button. | An error message "Invalid email or password!" | An error message "Incorrect password" is displayed |  | An error message "Incorrect password" is displayed
24 | Signing In | The user is not logged in to the system. | User leaves email field as empty. User presses Submit button. | An error message "Email field cannot be empty. Please enter your email." | An error message displayed "Email filed cannot by empty" |  | An error message displayed "Email filed cannot by empty"
25 | Signing In | The user is not logged in to the system. | User leaves password field as empty. User presses submit button | An error message "Password field cannot be empty. Please enter your password" | An error message "Password field cannot be empty" |  | An error message "Password field cannot be empty"
26 | Trends page | The user is logged in to the system. | User navigates to trends page. | Display trending clothing items scraped from the web. | Part of R2 submission |  | The latest trending items scraped are shown.
27 | Trends Scraper | The user is the admin. | Admin runs new_scrapper.py : the latest trend scraper script | The folder scraped_images dedicated to store latest trend images is fillled with 20 latest fashion images from the web | Part of R2 submission |  | The folder scraped_images dedicated to store latest trend images is fillled with 20 latest fashion images from the web
28 | Navigation Options | The user is on the home page | The user clicks on the 'View trends' button | The user should be on the 'view trends' page | The user is on "Trends" page |  | The user is on "Trends" page
29 | Navigation Options | The user is logged in. The user is on the home page. | The user clicks on the 'View wardrobe' button | The user is able to view the wardrobe. | The user is on "Wardrobe" page |  | The user is on "Wardrobe" page
30 | Navigation Options | The user is not logged in. The user is on the home page | The user clicks on the 'View wardrobe' button | The user is prompted to sign up or sign in. | View Wardrobe button is not visible if the user is not signed in |  | Required outcome was changed to be prompted to login directly when not logged in
31 | Navigation Options | The user is logged in. The user is on the home page. | The user clicks on the 'Get recommendations' button | The user is directed to the 'get recommendations' page. | The user is on the "Recommendations" page |  | The user is on the "Recommendations" page
32 | Navigation Options | The user is not logged in. The user is on the home page | The user clicks on the 'Get recommendations' button | The user is prompted to sign up or sign in. | Get Recommendations button is not visible if user has not logged in |  | Required outcome was changed to be prompted to login directly when not logged in
33 | Navigation Options | The user is not logged in to the system and is on the home screen | The user clicks on the 'login' button | The user is prompted to sign up or sign in | The user is on sign in page |  | The user is on sign in page
34 | Logging out | User has logged into their account | The user clicks the log out button | The user is logged out of their account and returns to the home screen displayed for users who are not logged in | The user gets logged out and is on home screen |  | The user gets logged out and is on home screen
35 | Add to favorites | User is viewing the wardrobe page | User clicks the Add to Favorites button beside 'Dress X' | Dress X gets added to favorites and gets displayed alongside other favorites when 'favorites' option is selected in filters and also on the Home Screen. | The item is added to favourites |  | The item is added to favorites.
36 | Recommendations Page | User has signed in and wardrobe has atleast 1 dress | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of top and bottom according to occasion which is recommended. | Part of R2 submission |  | The recommendations page, after some loading, shows the dress pair of top and bottom according to occasion which is recommended.
37 | Recommendations Page | User has signed in and wardrobe has only dresses which are worn on top. | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended. | Part of R2 submission |  | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended.
38 | Recommendations Page | User has signed in and wardrobe has only dresses which are worn on bottom. | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of bottom only according to occasion which is recommended. | Part of R2 submission. |  | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended.
39 | Recommendations Page | User has signed in and wardrobe has no dresses | User inputs the prompt for their occasion in plain text. | A message is displayed that no clothes are found in the wardrobe. | Part of R2 submission |  | A message is displayed that no clothes are found in the wardrobe.
WEBSITE:
43 | Signing Up | The user is not logged in to the system in the website. | User attempts to sign up. User fails to provide email ID which is a mandatory field. | The system displays an error message prompting the user to fill in all required fields. | An error message "Fill out all fields" is displayed |  | An error message "Email is a required filed " is displayed
44 | Signing Up | The user is not logged in to the system in the website. An account by the email ID of temp@gmail.com already exists. | User attempts to sign up with temp@gmail.com as their email. | The system displays an error message indicating that the email is already in use. | An error message "User already exists" is displayed |  | An error message "User already exist" is displayed
45 | Signing Up | The user is not logged in to the system. | User successfully fills out the sign-up form with all required information. | The system creates a new user account and automatically logs in the user. | User redirected to the signin page |  | User redirected to the signin page
46 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded atleast 1 clothing item classified as Casualwear. | User navigates to the 'Wardrobe’ section and selects 'Casualwear' from the filter tags. | The system retrieves and displays the user's Casualwear clothes, as assigned by the ML model. | The user is displayed all clothes of the given tag |  | The user is displayed all clothes of the given tag
47 | Viewing Clothing Collection | The user is not logged in to the system. | User opens the website. | The system displays the current trending images to the user and prompts to login. | The trending images are not seen on the home page. |  | Current trending images are displayed and login button is displayed.
48 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded no clothing images yet. | User navigates to the "Clothing Collection" section. | The system prompts the user to upload clothing images. An 'Add New' button is presented. | 'Add new’ button is there but no prompt is shown. |  | A prompt is shown to tell the user to add their clothing items by pressing + which is Add New button.
49 | Viewing Clothing Collection | The user is logged in to the system. The user has uploaded no clothing item classified as casualwear. | User navigates to the 'Clothing Collection' section. User selects 'Casualwear' from the filter tags. | The system displays a message that no clothes match the given description. | No cloth items shown |  | The system displays a message that no clothes match the given description.
50 | Adding New Clothing Items | The user is logged in on the website. | The user clicks on the 'Add New' button. | The user is presented with the options 'Camera' and 'Gallery'. | The user can click a photo or upload from gallery |  | The user can click a photo or upload from gallery
51 | Adding New Clothing Items | The user is logged in on the website. | User navigates to the "Wardrobe" section. The user clicks on the 'Upload image' button. | The user is presented with the options 'Camera' and 'Gallery'. | The user can click a photo or upload from gallery |  | The user can click a photo or upload from gallery
52 | Adding New Clothing Items | User is logged in and has added clicked upload image button to add a new clothing item. | The user selects an image. | The image is displayed on the 'Wardrobe' section of the application, with tags assigned by the ML model. | The captured image is added to user's wardrobe. Random tags given |  | The captured image is added to the user’s wardrobe and tags assigned by ML model are shown.
53 | Deleting Clothing Items | There is atleast one clothing item present in wardrobe. | User presses the delete icon present on clothing item. User selects 'Yes' when prompted 'Are you sure?' | The selected item is successfully removed from database. The wardrobe updates immediately to reflect the removal of deleted item. | The item is deleted from user's wardrobe |  | The item is deleted from user's wardrobe
54 | Deleting Clothing Items | There is atleast one clothing item present in wardrobe. | User presses the delete icon present on clothing item. User selects 'No' when prompted 'Are you sure?' | The wardrobe remains unaffected. | The item is not deleted from user's wardrobe |  | The item is not deleted from user's wardrobe
55 | User Profile Customization | The user is logged in to the system. The user's password is 'abcdef' | User goes to 'Customize profile'. User selects 'Change password' option. User enters wrong old password, 'ABCDEF' | An error message "Wrong password" is displayed. The user is prompted to enter password again | Part of R2 submission |  | An error message "Wrong Old password" is displayed. The user is prompted to enter password again.
56 | User Profile Customization | The user is logged in to the system. The user's password is 'abcdef' | User goes to 'Customize profile'. User selects 'Change password' option. User enters correct old password 'abcdef', and a new password '123456' | The password of the profile is updated in the database to '123456' | Part of R2 submission |  | The password of the profile is updated in the database to '123456'
57 | User Profile Customization | The user is logged in to the system. The user's gender is set as Male. | User goes to Profile Page. User selects 'Other' as updated gender. The user saves changes. | The gender of the profile is updated in the database. | The gender of user is changed |  | The gender of user is changed
58 | User Profile Customization | The user is logged in to the system. The user's phone number is 9898989898. | User goes to Profile Page. In the mobile number field, user enters a 10 digit number, 9898989897. The user saves changes. | The phone number of the profile is updated in the database. | The phone number of user is changed |  | The phone number of user is changed
59 | User Profile Customization | The user is logged in to the system. The user's phone number is 9898989898. | User goes to Profile Page. In the mobile number field, The user enters a 9 digit number, 989898987. | An error message "Invalid Phone number" is displayed and the user is prompted to enter phone number again | An error message "Invalid field mobile" is displayed |  | An error message "Invalid field mobile" is displayed
60 | User Profile Customization | The user is logged in to the system. The user's name is set as 'Amit'. | User goes to Profile Page. In the Name field, The user enters a non-empty name, Amitabh. The user saves changes. | The name of the user is updated in the database | The name of the user is updated |  | The name of the user is updated
61 | Signing In | The user is not logged in to the system. | User enters valid email ID. User enters correct password. User presses Submit button. | User successfully logs in into the account | The user is logged in and is on home page |  | The user is logged in and is on home page
62 | Signing In | The user is not logged in to the system. | User enters invalid email. User preses submit button. | An error message "Invalid email or password!" | An error message "Email not registered" is displayed |  | An error message "Email not registered" is displayed
63 | Signing In | The user is not logged in to the system. | User enters valid email and incorrect password. User presses submit button. | An error message "Invalid email or password!" | An error message "Incorrect password" is displayed |  | An error message "Incorrect password" is displayed
64 | Signing In | The user is not logged in to the system. | User leaves email field as empty. User presses Submit button. | An error message "Email field cannot be empty. Please enter your email." | An error message displayed "Email filed cannot by empty" |  | An error message displayed "Email filed cannot by empty"
65 | Signing In | The user is not logged in to the system. | User leaves password field as empty. User presses submit button | An error message "Password field cannot be empty. Please enter your password" | An error message "Password field cannot be empty" |  | An error message "Password field cannot be empty"
66 | Trends page | The user is logged in to the system. | User navigates to trends page. | Display trending clothing items scraped from the web. | Part of R2 submission |  | The latest trending items scraped are shown.
67 | Navigation Options | The user is on the home page | The user clicks on the 'View trends' button | The user should be on the 'view trends' page | The user is on "Trends" page |  | The user is on "Trends" page
68 | Navigation Options | The user is logged in. The user is on the home page. | The user clicks on the 'View wardrobe' button | The user is able to view the wardrobe. | The user is on "Wardrobe" page |  | The user is on "Wardrobe" page
69 | Navigation Options | The user is not logged in. The user is on the home page | The user clicks on the 'View wardrobe' button | The user is prompted to sign up or sign in. | View Wardrobe button is not visible if the user is not signed in |  | A page prompting user to login is shown on the wardrobe page if the user is not signed in
70 | Navigation Options | The user is logged in. The user is on the home page. | The user clicks on the 'Get recommendations' button | The user is directed to the 'get recommendations' page. | The user is on the "Recommendations" page |  | The user is on the "Recommendations" page
71 | Navigation Options | The user is not logged in. The user is on the home page | The user clicks on the 'Get recommendations' button | The user is prompted to sign up or sign in. | Get Recommendations button is not visible if user has not logged in |  | A page prompting user to login is shown on the recommendations page if the user is not signed in
72 | Navigation Options | The user is not logged in to the system and is on the home screen | The user clicks on the 'login' button | The user is prompted to sign up or sign in | The user is on sign in page |  | The user is on sign in page
73 | Logging out | User has logged into their account | The user clicks the log out button | The user is logged out of their account and returns to the home screen displayed for users who are not logged in | The user gets logged out and is on home screen |  | The user gets logged out and is on home screen
74 | Add to favorites | User is viewing the wardrobe page | User clicks the Add to Favorites button beside 'Dress X' | Dress X gets added to favorites and gets displayed alongside other favorites when 'favorites' option is selected in filters and also on the Home Screen. | The item is added to favourites |  | The item is added to favorites.
75 | Recommendations Page | User has signed in and wardrobe has atleast 1 dress | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of top and bottom according to occasion which is recommended. | Part of R2 submission |  | The recommendations page, after some loading, shows the dress pair of top and bottom according to occasion which is recommended.
76 | Recommendations Page | User has signed in and wardrobe has only dresses which are worn on top. | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended. | Part of R2 submission |  | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended.
77 | Recommendations Page | User has signed in and wardrobe has only dresses which are worn on bottom. | User inputs the prompt for their occasion in plain text. | The recommendations page, after some loading, shows the dress pair of bottom only according to occasion which is recommended. | Part of R2 submission. |  | The recommendations page, after some loading, shows the dress pair of top only according to occasion which is recommended.
78 | Recommendations Page | User has signed in and wardrobe has no dresses | User inputs the prompt for their occasion in plain text. | A message is displayed that no clothes are found in the wardrobe. | Part of R2 submission |  | A message is displayed that no clothes are found in the wardrobe.

## Instructions
Test plan Instructions
It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests
Test No. | User Story covered | Preconditions | Test Description | Expected Outcome | R1 Outcome | R2 Outcome
1 | Move Player | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester1 | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located at Reading Railroad cell.
2 | Move Player | Test 1 completed | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located on Jail cell.
3 | Move Players in Turns | Game is in test mode. Game is in initial state. Number of Players: 2 Player 1 Name: Tester1 Player 2 Name: Tester2 | Player 1 Dice Roll: 5 Player 1 End Turn | Player 1 is located at Reading Railroad
|  |  | Player 2 Dice Roll: 3 Player 2 End Turn | Player 2 is located at Baltic Avenue
4 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 39 Player 1 End Turn | Player 1 is located at Boardwalk
|  |  | Verify Player 1 bank balance | Player 1 has $1500
5 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 40 Player 1 End Turn | Player 1 is located on GO cell
|  |  | Verify Player 1 bank balance | Player 1 has $1700 | Go money paid out only after passing GO, not when it is reached.
6 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 41 Player 1 End Turn | Player 1 is located at Mediterranean Avenue
|  |  | Verify Player 1 bank balance | Player 1 has $1700